## TEMPLATE
ARIZONA DEPARTMENT OF TRANSPORTATION
OFFICE MEMO
Date
TO: | JULIE E. KLIEWER, Ph.D., P.E.
Assistant State Engineer, Construction-Materials
| Construction Group 172A |  | Change the colored areas
to black on your finished
FROM: | Your Name |  | document.
Title
Mail Drop
THRU: | District Engineer Name |  | "Save as" to create a budget increase.
| Title |  | Remove my explanations on your
| Mail Drop |  | request before turning in.
This form contains formulas.
RE: | Project # / TRACS #
Project Name
Project Location
ORG: | xxxx
The referenced project requires additional work in order to adequately address the
construction needs at this location. Pertinent fiscal information is as follows:
Original Contract Amount: |  | 133909898 | This information is obtained from the CCS.
Five Percent Contingency: |  | 6695495 | Click UPDATE on the menu at the top. Click
Public Relations: |  | 75000 | FINANCE. When the report comes up, look in the
CE: |  | 10712792 | "Agreement Estimate" column. Delete the categories on this sheet
Post Design: |  | 1711114 | that don't apply. Do not make up categories.
Incentives: |  | 1542090 | If you have questions or cannot obtain a copy of the FINANCE report,
Other: |  | 1096000 | call Irene Montez at 602 712-7299.
DPS: |  | 74630
JPA's: |  | 0
Utilities: |  | 2330000
Original Available: |  | 158147019 | Should equal "Total:" in Agree. Est. column on Finance Report.
Actual costs are to be taken from the 125 column of Finance Screen
Actual Construction Costs: |  | 150441854.59 | Enter either "Contractor Pay" or "CPE Payments" whichever is greatest
Actual Other Construction: |  | 32193.56 | Enter Other Construction
Actual Public Relations: |  | 97774.42 | Enter Public Relations
Actual CE: |  | 6862968.84 | Enter Total CE
Actual Post Design: |  | 1866285.99 | Enter Total Post Design
Actual DPS: |  | 0 | Enter DPS
Actual JPAs: |  | 1096000 | Enter JPA'S
Actual Utilities: |  | 0 | Enter Utilities
Contract Work Remaining: |  | 392468 | You figure
Additional Other Construction: |  | 2474.02 | You figure | Do not make up additional
Additional Public Relations: |  | 0 | You figure
Additional Suppl. Agree: |  | 405000 | You figure | categories.
Additional CE Costs: |  | 0 | You figure | List only the lines you need
Additional Post Design: |  | 0 | You figure
Additional DPS: |  | 0 | You figure | in your request.
Additional JPAs: |  | 0 | You figure | Take out the categories you do not need.
Additional Utilities: |  | 0 | You figure
Additional Costs: |  | 0 | This line is used to round the total request amount to the nearest $5K
Proposed New Total Needed: |  | 161197019.42 | Formula in this cell. You don't need to enter anything here.
Less Previous Increases: |  | -2280000 | Enter as a Negative number total Previous Budget Increases to date.
Requested Amount: |  | 770000.42 | Formula in this cell. You don't need to enter anything here.
Reason for Increase: |  |  | Enter a detailed explanation for the additional funds being requested.
Do not use abbreviations. Attached additional back-up if necessary.
Funding Source: |  |  | Resident Engineer is responsible for contacting Julie Kliewer
regarding Contingency Funds. If the request is for a Local Government project
RE should work with local agency and Jodi Rooney, ADOT Local Government
Section to determine the funding source. Submit written statement from
local agency indicating agreement to cover the increase.
Procurement budget increases in excess of $100,00 must be approved
by the procurement officer. If applicable, field reports will forward
budget increase to procurement for signature.
I recommend that the budget for this project be increased to accommodate this additional work.
____________________________
RESIDENT ENGINEER
____________________________
XXX:xx |  |  | DISTRICT ENGINEER
cc: | Provide Name, Title, and Employer of Local Government or 3rd Party who agreed fund to the increase
Be sure to delete or backspace out all the explanation notes. Also your
finished document should be in black.
updated 6/9/16