## Hour Estimate
Contract No. XXXX-XXX.X0
Project Name
Tracs No. TBD
Company Name
TYPE OF WORK | [5 empty] | TOTAL | Proj. | Proj. | Sr . Proj. | Proj. | Proj. | CADD | Registered | Survey | Suvey | Clerical | 3-Person
|  |  | SCALE | NO. SHTS. | HRS/SHT | HOURS | Principal | Manager | Eng. | Eng. | Designer | Tech | Land Surveyor | Party Chief | Technician |  | Crew
[7 empty] | 1% | 7% | 30% | 40% | 22% | 0%
Progress Meetings/Coordination/Administration
|  | Project Kickoff Meeting (Phoenix) |  |  |  | 2 |  | 1 | 1
|  | Project Monthly Meetings /Combine with Stakeholder Mtgs (4) (See Scope - 3 meetings in Phoenix, 1 in Flagstaff) |  |  |  | 2 |  | 1 | 1
|  | Coordination and Comment Resolution (3) |  |  |  | 2 |  | 1 | 1
|  | Monthly Invoice (5 months duration) |  |  |  | 2 |  | 1 | [7 empty] | 1
Topographical Survey
|  | Set survey controls |  |  |  | 3 | [6 empty] | 1 | 1 | 1
|  | Perform topographical Survey |  |  |  | 3 | [6 empty] | 1 | 1 | 1
|  | Prepare control sheets |  | 1 | 3 | 3 | [5 empty] | 1 | 1 | 1
|  | Project Field Reviews (2) |  |  |  | 2 |  | 1 | 1
Roadway Box Culvert Extension
|  | General Notes and Design Sheets |  | 1 | 4 | 4 |  | 1 | 1 |  | 1 | 1
|  | Barrier Summary Sheet |  | 1 | 4 | 4 |  | 1 | 1 |  | 1 | 1
|  | Box Culvert Summary Sheet |  | 1 | 4 | 4 |  | 1 | 1 |  | 1 | 1
|  | Typical Detail Sheets Including Embankment/Grading Detail Plans |  | 1 | 6 | 6 |  | 1 | 1 | 1 | 1 | 1 |  |  |  | 1
|  | Plan and Profile Sheets - Box Culvert Extensions |  | 1 | 6 | 6 |  | 1 | 1 | 1 | 1 | 1 |  |  |  | 1
| * | Headwall Details (See Scope/Fee from [Subconsultant])
|  | SWPPP |  | 1 | 4 | 4 |  | 1 | 1 |  | 1 | 1
Traffic Control Plan
|  | General Notes, Details & Quantities |  | 1 | 4 | 4 |  | 1 | 1 |  |  | 1 |  |  |  | 1
|  | Maintenance of Traffic/Sequencing |  | 1 | 3 | 3 |  | 1 | 1 |  |  | 1
|  | Traffic Control Plans - Typical Details |  | 1 | 3 | 3 |  | 1 | 1 |  |  | 1
Pavement Marking & Signing
|  | General Notes & Quantities |  | 1 | 4 | 4 |  | 1 | 1 |  |  | 1 |  |  |  | 1
|  | Pavement Marking & Signing (Detail) |  | 1 | 3 | 3 |  | 1 | 1 |  |  | 1
|  | Cost & Quantity Estimation |  |  |  | 3 |  | 1 | 1 | [6 empty] | 1
|  | Special Provisions |  |  |  | 3 |  | 1 | 1 | [6 empty] | 1
|  | Contracts and Specifications Process |  |  |  | 3 |  | 1 | 1 | [6 empty] | 1
TOTAL TYPE OF WORK |  |  |  | 12 | 6.0833 | 73 | 0 | 19 | 18 | 2 | 6 | 12 | 3 | 3 | 2 | 8
|  |  |  | Avg hours/sht |  |  | 0% | 26.03% | 24.66% | 2.74% | 8.219% | 16.44% | 4.11% | 4.11% | 2.74% | 10.96%
TOTAL FOR PROJECT | [5 empty] | 73 | 0 | 19 | 18 | 2 | 6 | 12 | 3 | 3 | 2 | 8
[7 empty] | 0% | 26.03% | 24.66% | 2.74% | 8.219% | 16.44% | #DIV/0! | 15.79% | 11.11% | 42.11%
Avg hours/sht

## Summary
Contract No. XXXX-XXX.X0 | [5 empty] | Complete Name
Project Name
Tracs No. TBD
DERIVATION OF COST PROPOSAL SUMMARY
(Figures Rounded to the Nearest $1.00)
Estimated Direct Labor
|  |  | Est. Hourly |  | Estimated
Classification | Manhours |  | Rates |  | Cost
Project Principal | 0 |  | 1 |  | 0
Project Manager | 1 |  | 1 |  | 1
Senior Project Engineer | 1 |  | 1 |  | 1
Project Engineer | 1 |  | 1 |  | 1
Project Designer | 1 |  | 1 |  | 1
CADD Technician | 1 |  | 1 |  | 1
Secretary/Clerical | 1 |  | 1 |  | 1
Registered Land Surveyor | 1 |  | 1 |  | 1
Survey Party Chief | 1 |  | 1 |  | 1
Survey Technician | 1 |  | 1 |  | 1
TOTAL | 9
| Total Estimated Labor |  |  |  | 9
| Negotiated Overhead |  |  |  | 0.09
| (at | 1 | % of Direct Labor)
| Sub-Total |  |  |  | 9.09
Estimated Direct Expenses (at Estimated Actual Cost)
Printing/Reproduction |  |  | 0
Meals |  |  | 0
Mileage |  |  | 0
Lodging |  |  | 2
| Total Estimated Expenses |  |  |  | 2
Estimated Outside Services and Consultants (at Estimated Actual Cost)
Printing/Reproduction - GOS Products for Business |  |  |  |  | 0
| Total Estimated Outside Services |  |  |  | 0
Sub-Consultant Name (Structural Design - Box Culvert Transitions) |  |  |  |  | 0
| Fixed Fee @ | 0 | % |  | 0
(Direct Labor + Overhead x Multiplier)
Deduction from CM1
(reduced to 5 culverts. Removed striping and barrier plans)
| Total Lump Sum Costs |  |  |  | 11.09
Consultant Firm Signature |  |  |  | Date

## Direct Expenses
Contract No. XXXX-XXX.X0
Project Name
Tracs No. TBD
Company Name
REPRODUCTION
| Est. No. | No. of | No. of | Total
| of Shts. | Copies | Submittals | Sheets
8.5 X 11 Copies
(includes inhouse prints for QC, etc) |  |  |  | 0
Total 8.5 X 11 Copies |  |  |  | 0
at $0.10/copy |  |  |  | 0
11 X 17 Copies
(References Submittal Prints) |  |  |  | 0
Total 11 X 17 Copies |  |  |  | 0
at $0.10/copy |  |  |  | 0
22 X 34 Copies |  |  |  | 0
Total 22 X 34 Copies |  |  |  | 0
at $10.75/copy |  |  |  | 0
TOTAL FOR REPRODUCTION:
8.5x11 Copies |  |  |  | 0
11x17 Copies |  |  |  | 0
TOTAL REPRODUCTION (IN HOUSE) |  |  |  | 0
MEALS
| Cost/ | Est. of |  | Total
| Day | Number |  | Cost
Survey (two persons) | 0 | 1 |  | 0
Site Visit | 0 | 1 |  | 0
TOTAL MEALS |  |  |  | 0
MILEAGE
|  | Miles/ |  | Total
| Number | Trip | Total | Miles
Site Visit | 0 | 1 | 0
Project Meetings | 0 | 1 | 0
Topographical Survey | 0 | 1 | 0
|  |  | 0 | 0
TOTAL MILEAGE COST @ $0.001/MILE: |  |  |  | 0
LODGING
| Est. of | Cost/ |  | Total
| Number | Day |  | Cost
Survey (two rooms) | 1 | 1 |  | 1
Site Visit | 1 | 1 |  | 1
TOTAL LODGING: |  |  |  | 2
TOTAL DIRECT EXPENSES
Reproduction |  |  |  | 0
Meals |  |  |  | 0
Mileage |  |  |  | 0
Lodging |  |  |  | 2
TOTAL DIRECT EXPENSES |  |  |  | 2