## Fee Estimate
Project Name |  |  |  |  | Name of firm
ATTACHMENT B
DRAFT DERIVATION OF COST PROPOSAL SUMMARY
(Figures Rounded to the Nearest $1.00)
Estimated Basic SOW Fee
|  | Loaded Hourly |  | Estimated
Classification | Manhours | Rates |  | Cost
Project Principal | 13 | 1 |  | 13
QA/QC Manager | 20 | 1 |  | 20
Sr. Project Manager | 59 | 1 |  | 59
Sr. Project Engineer | 43 | 1 |  | 43
Project Engineer | 45 | 1 |  | 45
Engineer/Sr. Designer | 15 | 1 |  | 15
CADD Technician | 14 | 1 |  | 14
ITS Engineer |  | 108.91 |  | 0
Geotechnical Engineer |  | 125.41 |  | 0
Material Lab Supervisor |  | 107.59 |  | 0
Field Engineer |  | 92.97 |  | 0
Material Lab Technician |  | 55.15 |  | 0
Survey Manager (RLS) | 7 | 1 |  | 7
Survey Crew Chief | 4 | 1 |  | 4
Survey Crew (2 Person Crew) | 2 | 1 |  | 2
Inspector |  | 82.51 |  | 0
Project Coordinator | 46 | 1 |  | 46
Administrative Support | 18 | 1 |  | 18
TOTAL | 286
Total Estimated Basic SOW Labor Cost |  |  |  | 286
Scope Categories
Estimated Detailed SOW Fee (ALLOWANCES) | [5 empty] | Classification | A-Hours | B-Hours | D-Hours | E-Hours | Rates | Cost
Scope of Work |  |  |  | Value ($) |  | Project Principal | 0 | 0 | 0 | 11 | 1 | 11
A-Data Recon. (collect/ prepare title reports) |  |  |  | 6 |  | QA/QC Manager | 1 | 3 | 3 | 0 | 1 | 7
[6 empty] | Sr. Project Manager | 1 | 4 | 3 | 2 | 1 | 10
B-Util (calc. flows, prep paving, G&D, coord., util. |  |  |  | 20 |  | Sr. Project Engineer | 0 | 4 | 0 | 1 | 1 | 5
[6 empty] | Project Engineer | 1 | 2 | 0 | 0 | 1 | 3
D- Lot Cons/Platts (surv., legals & exhibits) |  |  |  | 20 |  | Engineer/Sr. Designer | 0 | 1 | 0 | 0 | 1 | 1
[6 empty] | CADD Technician | 0 | 0 | 2 | 0 | 1 | 2
E-Meetings/Outreach |  |  |  | 18 |  | ITS Engineer* | 0 | 0 | 0 | 0 | 1 | 0
Total Estimated Detailed SOW Labor Cost |  |  |  | 64 |  | Geotechnical Engineer* | 0 | 0 | 0 | 0 | 1 | 0
Estimated Direct Expenses (at Estimated Actual Cost) | [5 empty] | Material Lab Supervisor* | 0 | 0 | 0 | 0 | 1 | 0
[6 empty] | Field Engineer* | 0 | 0 | 0 | 0 | 1 | 0
Printing/Reproduction |  | 0 |  |  |  | Material Lab Technician* | 0 | 0 | 0 | 0 | 1 | 0
Outside Messenger Service |  | 0 |  |  |  | Survey Manager (RLS) | 1 | 0 | 3 | 1 | 1 | 5
Personal Mileage |  | 0 |  |  |  | Survey Crew Chief | 1 | 0 | 3 | 0 | 1 | 4
Supplies (Sur. + binders and foam core boards) |  | 1 |  |  |  | Survey Crew (2 Person Crew) | 0 | 0 | 2 | 0 | 1 | 2
[6 empty] | Inspector* | 0 | 0 | 0 | 0 | 1 | 0
| Total Estimated Expenses |  |  | 1 |  | Project Coordinator | 1 | 4 | 2 | 1 | 1 | 8
[6 empty] | Administrative Support | 0 | 2 | 2 | 2 | 1 | 6
| Sub-Total |  |  | 351 |  | Total Hours | 6 | 20 | 20 | 18 |  |  | 64
Outside Services and Consultants (Invoiced at-Cost) | [5 empty] | TOTAL ($) | 6 | 20 | 20 | 18 |  | 64
Traffic Count | Not considered | [10 empty] | 64
Total Estimated Outside Services Fees |  |  |  | 0
Total Contract Amount w/ ALLOWANCES |  |  |  | 351
Consultant Firm Signature |  |  | Date

## Man Hour Estimates
ATTACHMENT - D
(PROPOSED MAN-HOUR ESTIMATES)
Name of firm
WORK ELEMENTS - COLOR CODED BY SCOPE CATEGORY | SCALE | NO. OF SHTS | HRS/ SHEET | TOTAL HOURS | Project Principal | QA/QC Manger | Sr. Project Manager | Sr. Project Engineer | Project Engineer | Engineer/ Sr. Designer | CADD Technician | ITS Engineer | Geotech Engineer | Material Lab Supervisor | Geotech Field Engineer | Material Lab Technician | Survey Manager (RLS) | Survey Crew Chief | Survey Crew (2-Person) | Field Inspector | Project Coordinator | Admin Support
BASIC SCOPE OF WORK
A - DATA RECONNAISSANCE, REVIEW & SUMMARIES
Infrastructure As-built Maps |  |  |  | 4 |  |  | 1 |  | 1 | 1 | [10 empty] | 1
GIS datasets and shape files |  |  |  | 4 |  |  | 1 | 1 | 1 | [12 empty] | 1
Quarter Section Maps to identify existing wet utilities and irrigation |  |  |  | 4 |  |  | 1 | 1 |  | 1 | [10 empty] | 1
COP Right-of-Way Maps. • COP Zoning Maps. • COP Aerial Photos. • Reinvent Phoenix Documentation |  |  |  | 4 |  |  | 1 |  |  | 1 | [6 empty] | 1 |  |  |  | 1
COP Zoning Maps |  |  |  | 3 |  |  |  | 1 | 1 | [11 empty] | 1
COP Aerial Photos |  |  |  | 4 |  |  | 1 |  | 1 | [7 empty] | 1 |  |  |  | 1
Reinvent Phoenix Documentation |  |  |  | 3 |  |  | 1 | 1 | [13 empty] | 1
Downtown Phoenix Comprehensive Transportation Plan |  |  |  | 3 |  |  | 1 |  | 1 | [12 empty] | 1
MC Parcel & Assessors Maps |  |  |  | 4 |  |  | 1 | [9 empty] | 1 | 1 |  |  | 1
Utility R/W, Easement & Prior Rights Verification |  |  |  | 5 |  |  | 1 | 1 | [8 empty] | 1 | 1 |  |  | 1
Area Drainage Master Plans |  |  |  | 4 |  |  |  | 1 | 1 | [7 empty] | 1 |  |  |  |  | 1
ADEQ Well Site Documentations |  |  |  | 3 |  |  |  | 1 |  | 1 | [11 empty] | 1
Traffic Count Data (Including Ped. & Transit) |  |  |  | 6 |  |  | 1 | 1 | 1 | 1 | 1 | [9 empty] | 1
Collision Data |  |  |  | 4 |  |  |  | 1 | 1 |  | 1 | [9 empty] | 1
MAG/ COP Travel Demand Forecast Data |  |  |  | 5 |  |  | 1 | 1 | 1 |  | 1 | [10 empty] | 1
On-street and Major Facilities On-site Parking Counts |  |  |  | 6 |  | 1 | 1 | 1 |  | 1 | 1 | [10 empty] | 1
Sidewalk/ Bicycle Lane Inventory |  |  |  | 4 |  |  |  | 1 | 1 |  | 1 | [10 empty] | 1
Transit Route Inventory |  |  |  | 4 |  |  |  | 1 |  | 1 | 1 | [9 empty] | 1
Area Transportation System Improvement Master Plan |  |  |  | 5 |  |  | 1 | 1 | 1 | [11 empty] | 1 | 1
Dry Utility Inventory |  |  |  | 3 |  |  |  | 1 |  | 1 | [10 empty] | 1
COP Complete Street Ordinance |  |  |  | 3 |  |  | 1 | 1 | [13 empty] | 1
COP Bicycle Master Plan |  |  |  | 3 |  |  | 1 | 1 | [13 empty] | 1
Catalog/ Summary of Data |  |  |  | 4 |  | 1 | 1 | 1 | [12 empty] | 1
Sub-totals |  |  |  | 92 | 0 | 2 | 16 | 18 | 11 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 13 | 11 | 92
B - SITE VISITS (Estimated 3 Different Times in 18 Months) |  |  |  | 4 |  |  | 1 | 1 | 1 | [12 empty] | 1 | 4
C - WET UTILITY INFRASTRUCTURE CONDITION ASSESSMENT AND ANALYSES
Water Lines (Main, Secondary and Lateral) |  |  |  | 5 | 1 | 1 | 1 | 1 | [12 empty] | 1
Sewer Lines (Main, Secondary and Lateral) |  |  |  | 5 | 1 | 1 | 1 | 1 | [12 empty] | 1
Storm Drain Lines (Main, Secondary and Lateral) |  |  |  | 6 | 1 | 1 | 1 | 1 | [12 empty] | 1 | 1
Irrigation Systems |  |  |  | 3 |  |  | 1 | 1 | [12 empty] | 1
Well Systems |  |  |  | 3 |  |  | 1 | 1 | [12 empty] | 1
Hydrology/ Hydraulic Study |  |  |  | 6 |  | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1
30% Preliminary Area Wet Utilities Analyses & Improvement Plans (Water, Sewer, Storm) - Based on no more than 10 Development Sites |  |  |  | 7 |  | 1 | 1 | 1 | 1 | 1 | 1 | [9 empty] | 1
Order of Magnitude Conceptual Wet Utility Cost Estimate |  |  |  | 3 |  | 1 | 1 |  | 1
Sub-totals |  |  |  | 38 | 3 | 6 | 8 | 7 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 38
D - DRY UTILITY INFRASTRUCTURE NEED ANALYSIS/ COORDINATION
Electric |  |  |  | 4 |  |  | 1 | 1 | 1 | [11 empty] | 1
Gas |  |  |  | 4 |  |  | 1 | 1 | 1 | [11 empty] | 1
Cable TV |  |  |  | 4 |  |  | 1 | 1 |  | 1 | [10 empty] | 1
Fiber Optics |  |  |  | 4 |  |  | 1 | 1 |  | 1 | [10 empty] | 1
Order of Magnitude Conceptual Dry Utility Cost Estimate |  |  |  | 4 |  | 1 | 1 |  | 1 | [11 empty] | 1
Sub-totals |  |  |  | 20 | 0 | 1 | 5 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 20
D - TRANSPORTATION INFRASTRUCTURE NEEDS
Multimodal Circulation Analysis
Pedestrian |  |  |  | 3 |  | 1 | 1 |  | 1
Bicycle |  |  |  | 3 | 1 |  | 1 |  | 1
Bus |  |  |  | 2 |  |  | 1 |  | 1
Vehicular |  |  |  | 4 | 1 | 1 | 1 |  | 1
Collision |  |  |  | 4 | 1 | 1 | 1 |  | 1
Develop SYNCHRO Network - Existing & Future Condition |  |  |  | 5 | 1 |  | 1 | 1 | 1 | [11 empty] | 1
Existing Condition Intersection LOS |  |  |  | 3 |  |  | 1 | 1 | 1
Future Travel Demand Forecast - MAG/COP/ACLReP |  |  |  | 5 | 1 |  | 1 | 1 | 1 | [12 empty] | 1
Future Condition Intersection LOS |  |  |  | 3 |  |  | 1 | 1 | 1
Develop VISSIM Simulation Model |  |  |  | 3 | 1 |  | 1 | 1
Parking Demand Analysis/ Requirement |  |  |  | 3 |  |  |  | 1 | 1 | [12 empty] | 1
Intersection Control Warrant Analysis |  |  |  | 2 |  |  |  | 1 | 1
Queue Analysis |  |  |  | 2 |  |  |  | 1 | 1
30% Preliminary Area Major Roadway Improvement Plan (Consideration given to Road Diet, Complete Street, etc.) |  |  |  | 7 | 1 | 1 | 1 | 1 |  | 1 | 1 | [9 empty] | 1
Order of Magnitude Conceptual Roadway Improvement Cost Estimate |  |  |  | 4 |  | 1 |  | 1 |  | 1 | [10 empty] | 1
Sub-totals |  |  |  | 53 | 7 | 5 | 11 | 10 | 12 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 53
E - ABANDONMENTS
Prepare Line Drawing Exhibits for Abandonment
Streets/ Alleys |  |  |  | 7 |  | 1 | 1 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  | 1
Right-of-Way/ Easements |  |  |  | 6 |  | 1 | 1 |  |  |  | 1 | [5 empty] | 1 | 1 | 1
Sub-totals |  |  |  | 13 | 0 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 1 | 0 | 13
F - MEETINGS, TEAM COORDINATION AND PUBLIC OUTREACH
Technical Task Coordination Meetings
Traffic Engineering (3) |  |  |  | 4 |  |  | 1 |  | 1 | [11 empty] | 1 | 1
MAG - Travel Demand Forecast (2) |  |  |  | 3 |  |  | 1 |  | 1 | [11 empty] | 1
Design, Construction Management - Water/ Sewer(4) |  |  |  | 3 |  |  | 1 |  | 1 | [11 empty] | 1
Drainage (2) |  |  |  | 3 |  |  | 1 |  | 1 | [11 empty] | 1
Electric Utility (2) |  |  |  | 3 |  |  | 1 |  | 1 | [11 empty] | 1
Gas Utility (2) |  |  |  | 3 |  |  | 1 |  | 1 | [11 empty] | 1
Cable TV (1) |  |  |  | 3 |  |  | 1 |  | 1 | [11 empty] | 1
Telephone (2) |  |  |  | 3 |  |  | 1 |  | 1 | [11 empty] | 1
Concept Plan Review/ Comment Resolution |  |  |  | 3 |  |  | 1 |  | 1 | [11 empty] | 1
Team Coord/ Update Meetings (5)- Mostly Teleconf |  |  |  | 4 | 1 |  | 1 |  | 1 | [11 empty] | 1
Stakeholder/ Public Involvement (2 meetings) |  |  |  | 4 | 1 |  | 1 |  | 1 | [11 empty] | 1
Aviation Subcommittee/ District 8 (3 meetings) |  |  |  | 4 | 1 |  | 1 |  | 1 | [11 empty] | 1
Color Graphic Board - Project Area/ Alternatives |  |  |  | 3 |  |  | 1 |  |  |  | 1 | [9 empty] | 1
Rendering of Typical Roadway Cross Sections |  |  |  | 1 | [6 empty] | 1
Sub-totals |  |  |  | 44 | 3 | 0 | 13 | 0 | 12 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 1 | 44
TECHNICAL MEMORANDA
Traffic Circulation Analysis and LOS (Existing & Future Conditions) |  |  |  | 4 |  | 1 |  | 1 |  |  | 1 | [9 empty] | 1
Drainage Technical Memo |  |  |  | 5 |  | 1 | 1 |  | 1 |  | 1 | [9 empty] | 1
Water, Sewer and Storm Technical Memo |  |  |  | 6 |  | 1 | 1 | 1 | 1 | [11 empty] | 1 | 1
Dry Utility Technical Memo |  |  |  | 7 |  | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1
Sub-totals |  |  |  | 22 | 0 | 4 | 3 | 3 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 22
TOTAL BASIC SCOPE OF WORK MAN-HOURS |  |  |  | 286 | 13 | 20 | 59 | 43 | 45 | 15 | 14 | 0 | 0 | 0 | 0 | 0 | 7 | 4 | 2 | 0 | 46 | 18 | 286
286
DETAILED/ ENHANCED SCOPE OF WORK (ALLOWANCE)
A - DATA RECONNAISSANCE, REVIEW & SUMMARIES
Secure/ Review & Prepare New Title Report for Consolidated Lots (assumed max. of 10) |  |  |  | 6 |  | 1 | 1 |  | 1 | [7 empty] | 1 | 1 |  |  | 1 |  | 6
B - UTILITY INFRASTRUCTURE NEEDS
Calculate Demand Flows for Consolidated Lots |  |  |  | 4 |  | 1 | 1 | 1 | [12 empty] | 1
Prepare Infrastructure Plans, Specifications and Estimates |  |  |  | 7 |  | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1
Prepare Site Paving, G&D Plans Consolidated Lots |  |  |  | 6 |  | 1 | 1 | 1 | 1 | [11 empty] | 1 | 1
Coordinate with Dry Utility for upgrades and improvements |  |  |  | 3 |  |  | 1 | 1 | [12 empty] | 1
Sub-totals |  |  |  | 20 | 0 | 3 | 4 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 20
C - TRANSPORTATION INFRASTRUCTURE NEEDS
n/a | [22 empty] | 0
D - LOT CONSOLIDATION ABANDONMENT & PLATTING
Perform Boundary/ ALTA Survey |  |  |  | 7 |  | 1 | 1 | [9 empty] | 1 | 1 | 1 |  | 1 | 1
Prepare Final R/W and Easement Maps |  |  |  | 5 |  | 1 | 1 |  |  |  | 1 | [5 empty] | 1 | 1
Prepare Legal Descriptions/ Plats |  |  |  | 8 |  | 1 | 1 |  |  |  | 1 | [5 empty] | 1 | 1 | 1 |  | 1 | 1
Sub-totals |  |  |  | 20 | 0 | 3 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 2 | 2 | 20
E - MEETINGS AND OUTREARCH
Lot Owners for Platting (assumed 5 Meetings) |  |  |  | 13 | 10 |  | 1 | [9 empty] | 1 |  |  |  |  | 1
City Council and Public Meetings (assumed 2 Meetings) |  |  |  | 5 | 1 |  | 1 | 1 | [12 empty] | 1 | 1
Sub-totals |  |  |  | 18 | 11 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 2 | 18
TOTAL DETAILED SCOPE OF WORK MAN-HOURS |  |  |  | 64 | 11 | 7 | 10 | 5 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 2 | 0 | 8 | 6 | 64
64
OVERALL TOTAL MAN-HOURS |  |  |  | 350 | 24 | 27 | 69 | 48 | 48 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 4 | 0 | 54 | 24 | 64
Note on A24: this involves gathering and summarizing in tables/ figures (does not include counting)
Note on A25: gather, summarize including collision diagrams
Note on A26: request from MAG, review and approve with COP, revise as necessary, tables/figures
Note on A27: will require physical site counts or use of aerials/ Google/ graphics
Note on A30: will include plan review
Note on A36: 1st visit = 6hrsx3; 2nd 4hrsx2, 3rd 4hrsx2 + drive times 3+2+2
Note on A39: Assess condition of systems, propose upgrade and or reconstruction.
Note on A45: perform analysis to develop conceptual designs - all 3 utilities
Note on A64: validate existing condition model
Note on G12: Streets/Signals/Electric/Gas/Cable TV/etc
Note on X11: involved with organizing/ filing and tracking

## Direct Expenses
ATTACHMENT C
Project Name
PROPOSED ESTIMATE OF DIRECT EXPENSES
Company Name
OUTSIDE REPRODUCTION
| Est. No. | No. of | No. of | Total
| of Shts.* | Copies | Submittals | Sheets
11 X 17 Copies @ $0.00 ea.
(includes inhouse prints for QC*, etc) | 1 | 1 | 1 | 1
1
0
22 X 34 Copies @ $00.00 ea.
(submittals/ reviews/ presentations) | 1 | 1 | 1 | 1
1
0
TOTAL FOR REPRODUCTION:
11x17 Copies |  |  |  | 0
22 x 34 Copies (Bond+)Vellum |  |  |  | 0
TOTAL REPRODUCTION |  |  |  | 0
OUTSIDE MESSENGER SERVICE
| Est. Cost/ |  |  | Total
| Delivery | Number |  | Cost
Messenger | 0 | 1 |  | 0
TOTAL OUTSIDE MESSENGER SERVICE: |  |  |  | 0
MILEAGE
Miles/
| Number | Trip | Total
Field Visit | 1 | 1 | 1
Technical Task Meetings | 1 | 1 | 1
Stakehold/ Public Meetings | 1 | 1 | 1
Survey Crew | 1 | 1 | 1
|  |  | Total Miles | 4
TOTAL MILEAGE COST @ $0.51/MILE: |  |  |  | 0
SUPPLIES
| Est. of | Cost/ |  | Total
| Number | Unit |  | Cost
Misc. Surveying Materials (Lump Sum) | 1 | 1 |  | 1
TOTAL SUPPLIES: |  |  |  | 1
TOTAL DIRECT EXPENSES
Outside Reproduction |  |  |  | 0
Outside Messenger Service |  |  |  | 0
Personal Mileage |  |  |  | 0
Supplies |  |  |  | 1
TOTAL DIRECT EXPENSES |  |  |  | 1