## 2025-011 Upcoming Ads
| Selected/Pending Selection | As of: 7/20/2026
No. | Project/eSTIP | Route | Beg. MP | District | Project Name | Type of Work | PM | Ad. Date | Posted on Upcoming | Notes | Consultant Firm Selected
1 | F0884 01D/ 105950 | SR 89A | 344.8 | NW | SR 89A East of East Avenue | Reconstruct Rockwall | Steve Boschen | 2026-01-05 | 2025-12-08 | Reference Docs 12/8 | NFra, Inc
2 | T0705 03D/ 105763 | Town of Clarkdale, Yavapai County |  | NC | N Broadway St and Luke Ln | Roadway Improvement | Beena Chakkarabavi | 2026-01-05 | 2025-12-08 | Reference Docs 12/9 | Ardurra
3 | F0888 01L/ 105763 | US89A | 524 | NC | US89A, MP 524-566 | Six Box Culvert Extensions | Sal Salahuddin | 2026-01-05 | 2025-12-08 | Reference Docs 12/9 | Parsons Transportation Group Inc.
5 | F0899 01D | SR87 | 252 | NC | SR 87 & Bonita St to SR 260 & Mud Springs Rd | Design for Right Turn Lane on SR 87 at SR 260 intersection in Payson | Wang (Austin) Song Shin | 2026-01-12 | 2025-12-08 | Reference Docs 12/8/25 | HDR Engineering, Inc
6 | T0717 03D/ 105786 | City of Glendale |  | Central | 67th Ave, Deer Valley to Pinnacle Peak | Widening/Reconstruction | Connie Corvalan | 2026-01-12 | 2025-12-08 | Reference Docs 12/8/25. Multi-select, Submit on T0717 | Burgess & Niple, Inc.
7 | T0724 03D/ 105788 | Town of Gilbert |  | Central | Higley Rd, Warner to Amber Ln | Widening/Reconstruction | Patrick O'Leske |  |  |  | Jacobs Engineering Group, Inc.
9 | T0722 03L | Town of Payson | N/A | NC | Payson Wildfire Evacuation Route | Scoping for New Roadway | Skye Gentile Bush | 2026-01-26 | 2025-12-15 | Reference Docs 12/15/25 | Jacobs Engineering Group, Inc.
10 | F0916 01D | I-10 | 142.8 | Central | 27th Ave to 12th Street | Improve Cross Streets | Lina Bearat | 2026-01-26 | 2025-12-22 | Reference Docs 12/22/25 | Michael Baker International,Inc.
8 | F0905 01D | SR 87 & SR 260 | 250.95 | NC | SR 87; BIA 101 - Forest Dr & SR 260; Payson Village - Tyler Parkway | ITS Improvements and Adaptive Signal Timing | Skye Gentile Bush | 2026-02-02 | 2025-12-15 | Reference Docs 12/15/25 | Jacobs Engineering Group, Inc.
13 | F0901 01D | US 160 | 419.5 | NE | Laguna Creek Bridge Wash | Erosion Control | Esmeralda Broyles Gonzalez | 2026-02-02 | 2026-01-07 | Reference Docs 1/7/26 | HDR Engineering, Inc
14 | F0915 01D | I-17 | 203.91 | Central | I-17; Dunlap - Camelback | Install Wrong Way Detection (WWD) System | Arash Ghazanfari | 2026-02-02 | 2026-01-07 | Reference Docs 2/2/26 | Kimley-Horn and Associates
4 | F0897 01L | US 70 | 380 | SE | Town of Duncan Franklin Rd | Scoping for RCB Improvements/Road Realignment | Wang (Austin) Song Shin | 2026-02-10 | 2025-12-08 | Reference Docs 12/8/25 | Kimley-Horn and Associates
11 | F0597 01D/103433 | SR 389 | 1 | NC | SR389 at Arizona Ave | Install traffic control system on SR 389 in Colorado City | Beena Chakkarabavi | 2026-02-10 | 2025-12-15 | Reference Docs 12/15/25 | EPS Group, Inc
12 | F0900 01L | SR 377 | 8 | NE | Phx Park Wash S of Dry Lake | Drainage Improvements | Esmeralda Broyles Gonzalez | 2026-02-10 | 2026-01-07 | Reference Docs 1/7/26 | GHD Inc.
18 | F0923 01L/ 105501 | US 60 | 345 | SE | Show Low to Vernon | Scoping | Scott Sayles | 2026-02-17 | 2026-02-02 | Reference Docs 2/4/26 | Dibble & Associates Consulting Engineers
19 | F0926 01L/ 105501 | US 60 | 198 | C | SR 88 to SR 79 Bypass | Scoping, update DCR | Scott Sayles | 2026-02-17 | 2026-02-02 | Reference Docs 2/4/26 | Jacobs Engineering Group, Inc.
15 | T0510 03D | Yavapai County | NW | 9.7 | Hassayampa River Bridge | Bridge Replacement | Chris Rodriguez | 2026-02-23 | 2026-01-12 | Reference Docs 1/12/26. Multi-select in order1st , 2nd, 3rd: T0514, T0510, T0511), Submit on T0514 Pine Creek Bridge | T.Y. Lin International, Inc.
16 | T0511 03D | Yavapai County | NW | 9.1 | Little Pine Creek Bridge | Bridge Replacement |  |  |  |  | Consor North America, Inc.
17 | T0514 03D | Yavapai County | NW | 7.4 | Pine Creek Bridge | Bridge Replacement |  |  |  |  | Civil & Environmental Consultants, Inc.
20 | F0924 01L/105503 | I-40 | 201 | NC | Country Club to Winona | Scoping | Steve Boschen | 2026-03-02 | 2026-02-02 | Reference Docs 2/4/26. Multi Select in order 1st SR64, 2nd I-40 SOI submit on SR64. | Stantec Consultants Services, Inc
21 | F0925 01L/105504 | SR 64 | 185 | NC | I-40 to Grand Canyon National Park | Scoping | Steve Boschen | 2026-03-02 | 2026-02-02 |  | Dibble & Associates Consulting
22 | T0744 03D/103799 | Town of Payson/CAG |  | NC | W Forest Dr, McLane Rd to SR 87 | New Roadway | Judah Cain | 2026-06-01 | 2026-03-23 | Reference Docs 3/23 | Civil & Environmental Consultants, Inc. (CEC)
23 | T0746 03D/106031 | City of Casa Grande/SCMPO |  | SC | Viola St, Pinal Ave to Casa Grande Ave | Multi-Use Path | Judah Cain | 2026-06-15 | 2026-03-23 | Reference Docs 3/23 | Civil & Environmental Consultants, Inc. (CEC)
24 | F0936 01D | US 93 | 0 | NW | Hoover Dam - Householder Pass (MP 0 to MP 17.3) | Pavement Rehabilitation | Steve Boschen | 2026-05-11 | 2026-04-14 | Multi Selection. Consultants shall submit their proposal on US 93 (F0936) to be considered for one of the five projects. The top five consultants will be awarded one project each in the following order: F0936, F0940, F0943, F0942 and F0935 | Burgess & Niple, Inc
25 | F0940 01D | SR 387 | 0 | SC | SR 84/SR 287 - I-10 (MP 0 to MP 8.3) | Pavement Rehabilitation | Floyd Roehrich | 2026-05-11 | 2026-04-14 |  | Parsons Transportation Group, Inc.
26 | F0943 01D | US 60 | 246 | SE | Pineway St - Santee St (MP 246 to MP 250) | Pavement Rehabilitation | Beena Chakkarabavi | 2026-05-11 | 2026-04-14 |  | Jacobs Engineering Group, Inc.
27 | F0942 01D | SR 95 | 142.5 | SW | State Line - Shea Rd (MP 142.5 to 144.7) | Pavement Rehabilitation | Floyd Roehrich | 2026-05-11 | 2026-04-14 |  | Stantec Consultants Services, Inc.
28 | F0935 01D | US 60 | 236.1 | SE | County Line - Mtn Breeze Memorial Gardens (MP 236.1 to MP 240) | Pavement Rehabilitation | Beena Chakkarabavi | 2026-05-11 | 2026-04-14 |  | T.Y. Lin International, Inc.
29 | T0763 03D/105777 | City of Tempe/MAG |  | C | Broadway Rd 55th St to Mill Ave Tempe | Sidewalk and pavement improvements | Scott Sayles | 2026-06-15 | 2026-04-27 | Referance Docs 4/27 | Kimley-Horn & Associates, Inc.
PDOC 2025-011
As of: 7/20/2026
FUTURE ADVERTISEMENTS
No. | Project/eSTIP | Route/Local | Beg. MP | District | Project Name | Type of Work | PM | Ad. Date | Posted on Upcoming | Notes
30 | T0650 | Pinal County |  | Central | Thompson Rd and Mountain Vista Blvd, | Traffic Signal | Beena Chakkarabavi | 2026-07-27 | 2026-07-06 | HSIP Funds
31 | F0871 | I-10 | 125 | Central | I-10 L303 to L101, Ramp Meters | Install Ramp Meters | Chris Moore | 2026-08-10 | 2026-07-20
32 | T0660 | Coconino County |  | NC | Leupp Rd and Forest Rd 244A | Construct Left Turn Lane | Skye Gentile Bush | 2026-08-10 | 2026-07-20 | HSIP Funds
33 | F0880 | SR77 | 89.5 | SC | N of Saddlebrooke Blvd | Dynamic Messaging Sign | Vivian Li | 2026-08-10 | 2026-07-20
34 | T0683 | Mohave County |  | NW | White Hills Rd; Mineral Rd to Skipper Blvd | Install 5’ shoulders and rumble strips | Olivier Mirza | 2026-08-24 | 2026-07-20 | HSIP Funds